## Sheet1
Scope of Work and Remodel Estimate
By Emily Yang @ Seattle
Address | 10860 14th Ave S Seattle, WA 98168 | Column1
Bedroom/Bathroom | 3 Beds + 1 Bath
Sqft | 1320
Built year | 1943
Garage | 2 Carport
买入价 | 200K
预计ARV | 460K
Remodel Assumption | 1）这个房子属于低收入区，周边房价不高，因此在确定方案时不宜做过多装修，应该和周围房子相似，可以稍微好一点点，不要over spend
2）原则是能够修理的部件尽量修理，除非万不得已不用换新的
3）能够不拆墙就不拆墙，否则牵涉找工程师画图、申请permit，会大大拖延工期
Exterior
Column1 | Scope of work | Budget
Roof | 目测屋顶shingle还能使用，Presssure wash去除青苔。如果一定要换shingle，大约1400sqft，材料加人工大约3000 | 500
Exterior paint | Presssure wash + repaint 2 colors | 2500
Gutter | 目测gutter还能使用 | 0
Siding | 看样子可以不用换，局部可能需要patch | 300
Landscaping | Clean up | 500
Windows+sliding door | Replace with new. 8 windows x $350 = 2800. 1 sliding door $700. Window/door trim $500 | 4000
Permit | 假设不动墙，只申请电和水的permit | 600
Engineer | 不用画图纸 | 0
Interior
Column1 | Scope of work | Budget
Demo+dump | 5 dumps x $700= $3500, labor $1000 | 4500
Plumbing | Rough plumbing and finish plumbing, replace with new. | 2000
Water heater | 40 gal water heater | 600
Electrical | Panel upgrade to 200 A, $2000. 假设电线尚可以使用. Replace all outlets, switch. Install light fixture | 4000
HAVC | Assume still functionally working，需要做一次维护 | 300
Insulation | Assume still functionally working | 0
Drywall | Living room需要加一层drywall，大约44 sheet。绿色卧室墙面状况糟糕，可能需要skimcoat $300. Patch其他所有墙面 | 2412
Interior paint | 3 color, wall preparation. Paint ceiling, wall, door, trim. | 4000
Millwork | Baseboard, door trim, window trim | 2000
Interior door | 6 doors x $200 | 1200
Exterior door | 3 doors x $300 | 900
Kitchen cabinet + countertop | white + quartz | 7500
Kitchen appliance | 4 pieces | 2500
Floor | Install LVP in whole house. 1320 x $4 = 5280 | 5280
Bathroom | 1 tub, 1 vanity, 1 toilet, tile floor, tile wall | 3500
Sub total |  | 49092
Contingency | 15%
Total |  | 56455.8