## Sheet1
Phase I |  | duration
| Survey | 0
| construction drawing | 7
| Permit | 7
| Demolish (including shed) | 3
0
| foundation | 0
| water proof | 0
| Utility(electricicy and gas) | 3
| Sewage tank | 0
| Mold control | 2
| Termite control | 1
| Tree cutting | 1
| extra | 2 | Phase II | Frame and structure | 7
|  |  |  | windows | 1
| total | 14 |  | exterior wall painting | 3
|  |  |  | roof | 2
|  |  |  | gutter | 1
|  |  |  | water rough in | 1
|  |  |  | electric rough in | 1
|  |  |  | gas rough in | 1
|  |  |  | extra | 1 | Phase III | electrician | 7
[7 empty] | plumbing | 7
|  |  |  | total | 10 |  | deck/patio | 0
[7 empty] | doors | 1
[7 empty] | insulation | 1
[7 empty] | dry wall | 3
[7 empty] | trim | 2
[7 empty] | garage door | 0
[7 empty] | car port | 2
[7 empty] | HVAC | 2
[7 empty] | extra | 2 | Phase IV | painting | 3
[10 empty] | floor/carpet | 3
[7 empty] | total | 12 |  | cabinet/countertop | 2
[10 empty] | electrician finish | 1
[10 empty] | plumbing finish | 1
[10 empty] | driveway/sidewalk | 1
[10 empty] | landscaping | 1
[10 empty] | fence | 2
[10 empty] | final inspection | 1
[10 empty] | extra | 2
total